## GanttChart
Project Schedule
Group Members: Himanshi Manglunia, Kalpita Raut, Laura Walker
| Project Start Date | 2018-09-27
| ALL | Himanshi Manglunia |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Kalpita Raut | Laura Walker | [6 empty] | 2018-09-24 | [6 empty] | 2018-10-01 | [6 empty] | 2018-10-08 | [6 empty] | 2018-10-15 | [6 empty] | 2018-10-22 | [6 empty] | 2018-10-29 | [6 empty] | 2018-11-05 | [6 empty] | 2018-11-12
 | time axis 2018-09-24 to 2018-11-18
# | Task | Person | PREDECESSOR | Start Date | End Date | Days | % Done | Work Days | time axis 2018-09-24 to 2018-11-18
1 | Work Plan |  |  |  | - |  |  | -
1.1 | Analysis and Structuring | ALL |  | 2018-10-02 | 2018-10-02 | 0 | 100% | 1
1.2 | Materializing and Planning | ALL |  | 2018-10-03 | 2018-10-03 | 0 | 90% | 1
1.3 | Documentation | Himanshi Manglunia |  | 2018-10-02 | 2018-10-05 | 3 | 90% | 4
1.4 | [Task] |  |  | 2018-02-01 | 2018-02-04 | 4 | 75% | 2
1.4.1 | [Sub-task] |  |  | 2018-02-02 | 2018-02-03 | 2 | 50% | 1
1.4.2 | [Sub-task] |  |  | 2018-02-04 | 2018-02-06 | 3 | 50% | 2
1.5 | [Task] |  |  | 2018-02-05 | 2018-02-09 | 5 | 0% | 5
1.6 | [Task] |  |  | 2018-02-03 | 2018-02-09 | 7 | 0% | 5
1.7 | [Task] |  |  | 2018-02-10 | 2018-02-16 | 7 | 0% | 5
2 | Data Cleaning and Documentation Draft |  |  |  | - |  |  | -
2.1 | Work on feedback of previous task | ALL |  | 2018-10-07 | 2018-10-10 | 3 | 0% | 3
2.2 | Data Segregation and compilation | Laura Walker |  | 2018-10-10 | 2018-10-14 | 4 | 0% | 3
2.3 | Data Wrangling | Himanshi Manglunia |  | 2018-10-15 | 2018-10-19 | 4 | 0% | 5
2.4 | Data Cleaning | Laura Walker |  | 2018-10-20 | 2018-10-24 | 4 | 0% | 3
2.5 | Data Preparation | Kalpita Raut |  | 2018-10-25 | 2018-10-29 | 4 | 0% | 3
2.6 | Documentation | Kalpita Raut |  | 2018-10-30 | 2018-11-01 | 2 | 0% | 3
3 | R Script Draft |  |  |  | - |  |  | -
3.1 | Work on feedback of previous task | ALL |  | 2018-11-05 | 2018-11-07 | 2 | 0% | 3
3.2 | Data Wrangling R Script | Himanshi Manglunia |  | 2018-11-07 | 2018-11-09 | 2 | 0% | 3
3.3 | Data Cleaning R Script | Laura Walker |  | 2018-11-09 | 2018-11-11 | 2 | 0% | 1
3.4 | Data Preparation R Script | Kalpita Raut |  | 2018-11-11 | 2018-11-13 | 2 | 0% | 2
3.5 | Final documentation of all Scripts | Laura Walker |  | 2018-11-13 | 2018-11-15 | 2 | 0% | 3
4 | R Plot Draft |  |  |  | - |  |  | -
4.1 | Work on feedback of previous task | ALL |  | 2018-11-15 | 2018-11-15 | 1 | 0% | 1
4.2 | R Plot research question 1 | Laura Walker |  | 2018-11-17 | 2018-11-17 | 1 | 0% | 0
4.3 | R Plot research question 2 | Laura Walker |  | 2018-11-19 | 2018-11-19 | 1 | 0% | 1
4.4 | R Plot research question 3 | Laura Walker |  | 2018-11-21 | 2018-11-21 | 1 | 0% | 1
4.5 | Final documentation of all Scripts |  |  | 2018-11-23 | 2018-11-23 | 1 | 0% | 1
5 | Presentation |  |  |  | - |  |  | -
5.1 | Work on feedback of previous task | ALL |  | 2018-11-15 | 2018-11-15 | 1 | 0% | 1
5.2 | Structure the presentation | ALL |  | 2018-11-17 | 2018-11-17 | 1 | 0% | 0
5.3 | Compilation of all tasks | Himanshi Manglunia |  | 2018-11-19 | 2018-11-19 | 1 | 0% | 1
5.4 | Editing the presentation | Laura Walker |  | 2018-11-21 | 2018-11-21 | 1 | 0% | 1
6 | Git Package |  |  |  | - |  |  | -
6.1 | Commit all documentations | Himanshi Manglunia |  | 2018-11-26 | 2018-11-29 | 1 | 0% | 4
6.2 | Commit R Script Drafts | ALL |  | 2018-11-26 | 2018-11-29 | 1 | 0% | 4
6.3 | Commit R Plot Drafts | ALL |  | 2018-11-28 | 2018-11-29 | 1 | 0% | 2
6.4 | Commit final presentation | Kalpita Raut |  | 2018-11-28 | 2018-11-29 | 1 | 0% | 2
7 | Administrivia |  |  |  | - |  |  | -
7.1 | Meeting with instructor | ALL |  | 2018-11-01 | 2018-11-01 | 0 | 0% | 1
7.2 | Member out of town for conference | Laura Walker |  | 2018-11-03 | 2018-11-06 | 3 | 0% | 2
7.3 | Member out of town for work meeting | Laura Walker |  | 2018-10-24 | 2018-10-26 | 2 | 0% | 3
7.4 | Commit final presentation | Kalpita Raut |  | 2018-11-28 | 2018-11-29 | 1 | 0% | 2